## 1. Design Targets
Vehicle Design and Peformance Targets
Sr. No. | Items | Details
1 | Team ID | 21032
2 | Team Name | E-Chetak
3 | Kerb Weight (kg): | 136.42Kg
4 | Length (mm): | 2332 mm
5 | Length (inch): | 91.811 in
6 | Width (mm): | 1330 mm
7 | Width (Inch): | 52.362 in
8 | Height (mm): | 1500 mm
9 | Height (inch): | 59 in
10 | Max speed (km/h): | 40 km/h
11 | Maximum acceleration (m/s2): | 0.95 m/s2
12 | Grade-abilit (degree): | 12°
13 | Turning radius (m): | 3.6 m
14 | Turning radius (inch): | 141.276 in
15 | Battery Runime (Minutes): | 100 min

## 2. Project Plan
Efficycle Project Plan |  |  |  | Team ID |  | 21032 |  |  |  |  | Legends |  |  | Main Task/ Activity
Sub Task/ Activity
|  |  |  | Team Name |  | E-chetak | [7 empty] | Milestone
Milestone Details
Task ID | Task/Activity Description | Duration (Days) | Start Date | End Date | Responsible | Wk 01 | Wk 02 | Wk 03 | Wk 04 | Wk 05 | Wk 06 | Wk 07 | Wk 08 | Wk 09 | Wk 10 | Wk 11 | Wk 12 | Wk 13 | Wk 14 | Wk 15 | Wk 16 | Wk 17 | Wk 18 | Wk 19 | Wk 20 | Wk 21 | Wk 22 | Wk 23 | Wk 24 | Wk 25 | Wk 26 | Wk 27 | Wk 28 | Wk 29 | Wk 30 | Wk 31 | Wk 32 | Wk 33 | Wk 34 | Wk 35 | Wk 36 | Wk 37 | Wk 38 | Wk 39 | Wk 40 | Wk 41 | Wk 42
[6 empty] | 02/05 | 09/05 | 16/05 | 23/05 | 30/05 | 06/06 | 13/06 | 20/06 | 27/06 | 04/07 | 11/07 | 18/07 | 25/07 | 01/08 | 08/08 | 15/08 | 22/08 | 29/08 | 05/09 | 12/09 | 19/09 | 26/09 | 03/10 | 10/10 | 17/10 | 24/10 | 31/10 | 07/11 | 14/11 | 21/11 | 28/11 | 05/12 | 12/12 | 19/12 | 26/12 | 02/01 | 09/01 | 16/01 | 23/01 | 30/01 | 06/02 | 13/02
A | Basics | 49 | 2021-05-01 | 2021-06-19 | SHIVA
A.1 | Promotion of Effi-Cycle Season -12 | 14 | 2021-05-01 | 2021-05-15 | Azaj
A.2 | Team Formation | 7 | 2021-05-16 | 2021-05-23 | Shiva
A.3 | Final team list out | 1 | 2021-05-24 | 2021-05-25 | Shiva
A.4 | Team induction Programme | 5 | 2021-05-25 | 2021-05-30 | Prof PV Dorlikar
A.5 | Discussion of the segment Effi-Que with the team | 6 | 2021-06-01 | 2021-06-07 | Pravin
A.6 | Team registration | 2 | 2021-06-09 | 2021-06-11 | Pravin
A.7 | Allotment of departments | 1 | 2021-06-09 | 2021-06-10 | Azaj
A.8 | Project Plan layout | 5 | 2021-05-10 | 2021-05-15 | Azaj
A.9 | Vehicle Sketching by each member | 2 | 2021-06-09 | 2021-06-11 | Pravin
A.10 | Basic Software learning by each member | 9 | 2021-06-11 | 2021-06-20 | Azaj
A.11 | Study of Fundamental of Subsystems | 14 | 2021-06-11 | 2021-06-25 | Pravin
A.12 | Rulebook review & Explanation | 4 | 2021-06-15 | 2021-06-19 | Pravin
B | Sub-Systems Study and calculations | 21 | 2021-06-19 | 2021-07-10 | Pravin
B.1 | Roll Cage Design & Calculations | 4 | 2021-06-19 | 2021-06-23 | Azaj
B.1.1 | Setting the parameters according to Ergonomics/Rulebook | 5 | 2021-06-23 | 2021-06-28 | Harsh
B.1.2 | Selection of material for Roll Cage | 5 | 2021-06-23 | 2021-06-28 | Azaj
B.1.3 | Study of various Welding techniques | 2 | 2021-06-28 | 2021-06-30 | Azaj
B.1.4 | Pencil sketching of Roll Cage | 2 | 2021-06-28 | 2021-06-30 | Harsh
B.2 | Power Train | 21 | 2021-06-19 | 2021-07-10 | Pravin
B.2.1 | Force calculation on vehicle | 4 | 2021-06-19 | 2021-06-23 | Pravin
B.2.2 | Motor & power calculations | 7 | 2021-06-23 | 2021-06-30 | Prashant
B.2.3 | Selection of battery | 9 | 2021-07-01 | 2021-07-10 | Pravin
B.2.4 | Designing of gear integration | 9 | 2021-07-01 | 2021-07-10 | Arin
B.2.5 | Design of electric circuits | 21 | 2021-06-19 | 2021-07-10 | Saloni
B.3 | Suspension & Wheel Assembly | 21 | 2021-06-19 | 2021-07-10 | Vaibhav
B.3.1 | Wheel parameters | 5 | 2021-06-19 | 2021-06-24 | Kartik
B.3.2 | Type of Suspension | 6 | 2021-06-19 | 2021-06-25 | Vaibhav
B.3.3 | Damper calculations | 14 | 2021-06-26 | 2021-07-10 | Arunima
B.3.4 | Wishbones calculations | 14 | 2021-06-26 | 2021-07-10 | Vaibhav
B.3.5 | Knuckle Force calculations | 14 | 2021-06-26 | 2021-07-10 | Arunima
B.4 | Braking System | 21 | 2021-06-19 | 2021-07-10 | Kartik
B.4.1 | Static & Dynamic calculation on vehicle | 6 | 2021-06-19 | 2021-06-25 | Kartik
B.4.2 | Wheel lock analysis | 5 | 2021-06-25 | 2021-06-30 | Arin
B.4.3 | Disc, caliper & lever calculations | 9 | 2021-07-01 | 2021-07-10 | Arin
B.5 | Steering System | 21 | 2021-06-19 | 2021-07-10 | Arpit
B.5.1 | Steering Geometry selection | 6 | 2021-06-19 | 2021-06-25 | Abhay
B.5.2 | Static & Dynamic calculation of steering | 5 | 2021-06-25 | 2021-06-30 | Arpit
B.5.3 | Force calculation Handle | 9 | 2021-07-01 | 2021-07-10 | Abhay
B.5.4 | Study of rack and pinion | 9 | 2021-07-01 | 2021-07-10 | Arpit
B.6 | Advance technology | 21 | 2021-06-19 | 2021-07-10 | Saloni
B.6.1 | Types ADAS | 6 | 2021-06-19 | 2021-06-25 | Azaj
B.6.2 | Sensors study | 5 | 2021-06-25 | 2021-06-30 | Saloni
B.6.3 | Arduino | 9 | 2021-07-01 | 2021-07-10 | Saloni
B.6.4 | Infotainment | 9 | 2021-07-01 | 2021-07-10 | Saloni
C | Designing of Roll Cage CAD | 39 | 2021-06-11 | 2021-07-20 | Azaj
C.1 | Initial Roll cage Design by each member as per their dream Efficycle | 7 | 2021-06-11 | 2021-06-18 | Azaj
C.1.1 | Team meet for selection the best designs of roll cage | 1 | 2021-06-18 | 2021-06-19 | Harsh
C.1.2 | Noting all the innovative points of roll cage design | 15 | 2021-06-16 | 2021-07-01 | Azaj
C.1.3 | Human CAD according to Driver | 6 | 2021-06-25 | 2021-07-01 | Harsh
C.1.4 | Design of Roll Cage | 9 | 2021-07-01 | 2021-07-10 | Azaj
C.1.5 | Going through Ergonomics of Driver | 2 | 2021-07-10 | 2021-07-12 | Azaj
C.1.6 | Roll cage modification | 8 | 2021-07-12 | 2021-07-20 | Azaj
C.1.7 | Making mounting points for Suspension, battery, seat, motor etc | 8 | 2021-07-12 | 2021-07-20 | Azaj
D | Market availability and Procurement of Part | 9 | 2021-07-01 | 2021-07-10 | Pravin
D.1 | Roll Cage material | 9 | 2021-07-01 | 2021-07-10 | Azaj
D.2 | Transmission (Battery, motor, chain, pedal, Gearbox,sprockets etc..) | 9 | 2021-07-01 | 2021-07-10 | Prashant
D.3 | Suspension & wheel assembly (wheels, Dampers, Ball joints etc..) | 9 | 2021-07-01 | 2021-07-10 | Vaibhav
D.4 | Braking (Disc, caliper, master cylinder etc..) | 9 | 2021-07-01 | 2021-07-10 | Kartik
D.5 | Steering ( Gear Box, knuckle joints etc..) | 9 | 2021-07-01 | 2021-07-10 | Abhay
D.6 | ADAS (sensors, Arduino, wire harness etc..) | 9 | 2021-07-01 | 2021-07-10 | Saloni
D.7 | Electricals and accessories | 9 | 2021-07-01 | 2021-07-10 | Arunima
E | CAE Analysis of Roll cage | 30 | 2021-07-21 | 2021-08-20 | Azaj
E.1 | Analysis of Final design of roll cage (Dynamic + Static) - 01 | 16 | 2021-07-15 | 2021-07-31 | Azaj
E.2 | CFD of Vehicle -01 | 16 | 2021-07-15 | 2021-07-31 | Pravin
E.3 | Modification in Roll Cage for better strength and weight | 3 | 2021-08-02 | 2021-08-05 | Azaj
E.4 | Analysis on modified Roll Cage (Dynamic + static) -02 | 14 | 2021-08-06 | 2021-08-20 | Azaj
E.5 | CFD of Vehicle -02 | 5 | 2021-08-20 | 2021-08-25 | Pravin
E.6 | Final Roll cage ready | 5 | 2021-08-25 | 2021-08-30 | Azaj
F | Sub-systems CAD designs | 34 | 2021-07-12 | 2021-08-15 | Azaj
F.1 | Transmission | 34 | 2021-07-12 | 2021-08-15 | Pravin
F.1.1 | Motor & Gear Box | 18 | 2021-07-12 | 2021-07-30 | Pravin
F.1.2 | chain sprocket | 18 | 2021-07-12 | 2021-07-30 | Prashant
F.1.3 | Shaft and bearing | 15 | 2021-07-31 | 2021-08-15 | Pravin
F.1.4 | Crank & Pedal assembly | 15 | 2021-07-31 | 2021-08-15 | Prashant
F.2 | Suspension & Wheel Assembly | 34 | 2021-07-12 | 2021-08-15 | Vaibhav
F.2.1 | Rim & wheel assembly | 13 | 2021-07-12 | 2021-07-25 | Kartik
F.2.2 | A- Type Wishbones | 13 | 2021-07-12 | 2021-07-25 | Vaibhav
F.2.3 | Dampers | 21 | 2021-07-25 | 2021-08-15 | Arunima
F.2.4 | Ball joint & Fastners | 21 | 2021-07-25 | 2021-08-15 | Arunima
F.3 | Braking System | 34 | 2021-07-12 | 2021-08-15 | Kartik
F.3.1 | Disc & caliper | 20 | 2021-07-12 | 2021-08-01 | Arin
F.3.2 | Lever & master cylinder | 20 | 2021-07-12 | 2021-08-01 | Arin
F.3.3 | Brake fluid linings | 14 | 2021-08-01 | 2021-08-15 | Kartik
F.4 | Steering System | 34 | 2021-07-12 | 2021-08-15 | Arpit
F.4.1 | Handle | 34 | 2021-07-12 | 2021-08-15 | Azaj
F.4.2 | Rack & pinion | 34 | 2021-07-12 | 2021-08-15 | Arpit
F.4.3 | Tie rods | 34 | 2021-07-12 | 2021-08-15 | Abhay
F.4.4 | Extension rods | 34 | 2021-07-12 | 2021-08-15 | Arpit
F.5 | Advance technology & Electrics | 34 | 2021-07-12 | 2021-08-15 | Saloni
F.5.1 | Sensors | 34 | 2021-07-12 | 2021-08-15 | Arunima
F.5.2 | Arduino | 34 | 2021-07-12 | 2021-08-15 | Saloni
F.5.3 | LCD screen | 34 | 2021-07-12 | 2021-08-15 | Arunima
F.5.4 | Infotainment systems | 34 | 2021-07-12 | 2021-08-15 | Azaj
F.5.5 | Wire harness | 34 | 2021-07-12 | 2021-08-15 | Saloni
F.5.6 | Brake lights | 34 | 2021-07-12 | 2021-08-15 | Arin
F.6 | Miscellaneous | 34 | 2021-07-12 | 2021-08-15 | Harsh
F.6.1 | Doors | 34 | 2021-07-12 | 2021-08-15 | Harsh
F.6.2 | Side Mirrors | 34 | 2021-07-12 | 2021-08-15 | Harsh
F.6.3 | Head lights | 34 | 2021-07-12 | 2021-08-15 | Saloni
F.6.4 | Indicator lights | 34 | 2021-07-12 | 2021-08-15 | Harsh
F.6.5 | Brake lights | 34 | 2021-07-12 | 2021-08-15 | Harsh
F.6.6 | Seat | 34 | 2021-07-12 | 2021-08-15 | Azaj
F.6.7 | Seat belt | 34 | 2021-07-12 | 2021-08-15 | Harsh
F.6.8 | Fire extinguisher | 34 | 2021-07-12 | 2021-08-15 | Harsh
G | Simulations of Sub-Systems | 14 | 2021-08-01 | 2021-08-15 | Pravin
G.1 | Suspension & Steering on LOTUS | 14 | 2021-08-01 | 2021-08-15 | Vaibhav
G.2 | Transmission on Simulink | 14 | 2021-08-01 | 2021-08-15 | Pravin
G.3 | ADAS on Proteus | 14 | 2021-08-01 | 2021-08-15 | Saloni
0
H | CAE Analysis of Sub-Systems | 14 | 2021-08-01 | 2021-08-15 | Azaj
H.1 | Shafts | 14 | 2021-08-01 | 2021-08-15 | Prashant
H.2 | A-type Wishbones | 14 | 2021-08-01 | 2021-08-15 | Azaj
H.3 | Knuckle | 14 | 2021-08-01 | 2021-08-15 | Kartik
H.4 | Braking Disc (Thermal & Structural) | 14 | 2021-08-01 | 2021-08-15 | Arin
I | CAD Motion Study | 15 | 2021-08-10 | 2021-08-25 | Azaj
I.1 | Transmission chain Drive Motion study | 15 | 2021-08-10 | 2021-08-25 | Pravin
I.2 | Steering Rotations & adjustable mechanism | 6 | 2021-08-14 | 2021-08-20 | Arpit
I.3 | Wheel Motion | 11 | 2021-08-14 | 2021-08-25 | Arin
I.4 | Driver seat adjustment | 11 | 2021-08-14 | 2021-08-25 | Harsh
I.5 | Utility box motion | 11 | 2021-08-14 | 2021-08-25 | Azaj
I.6 | Door mechanism | 11 | 2021-08-14 | 2021-08-25 | Harsh
I.7 | Suspension travel | 11 | 2021-08-14 | 2021-08-25 | Arunima
J | Final vehicle assembly | 13 | 2021-09-05 | 2021-09-18 | Azaj
J.1 | Driver and Seat | 2 | 2021-09-05 | 2021-09-07 | Azaj
J.2 | Power Train | 3 | 2021-09-07 | 2021-09-10 | Pravin
J.3 | Suspension & Wheel assembly | 2 | 2021-09-10 | 2021-09-12 | Vaibhav
J.4 | Steering System | 2 | 2021-09-12 | 2021-09-14 | Arpit
J.5 | Braking | 2 | 2021-09-14 | 2021-09-16 | Kartik
J.6 | ADAS and electric components | 2 | 2021-09-16 | 2021-09-18 | Saloni
J.7 | Miscellaneous | 2 | 2021-09-16 | 2021-09-18 | Harsh
K | Submission of Design reports to Captain for Package-01 | 5 | 2021-09-15 | 2021-09-20 | Pravin
K.1 | Submission of Sub-Systems reports to captain | 1 | 2021-09-15 | 2021-09-16 | Bishkek
K.2 | Team discussion on DVP, BOM | 2 | 2021-09-16 | 2021-09-18 | Pravin
K.3 | Updating reports as per the team discussion | 2 | 2021-09-18 | 2021-09-20 | Pravin
K.4 | Submission of Package-01 | 1 | 2021-09-20 | 2021-09-21 | Pravin
L | IPG Car Maker | 32 | 2021-09-18 | 2021-10-20 | Azaj
L.1 | Training | 2 | 2021-09-18 | 2021-09-20 | Pravin
L.2 | Road modeling | 15 | 2021-09-20 | 2021-10-05 | Harsh
L.3 | Car Maker vehicle modeling | 15 | 2021-09-20 | 2021-10-05 | Azaj
L.4 | Scenario making | 5 | 2021-10-05 | 2021-10-10 | Harsh
L.5 | Data Analysis | 5 | 2021-10-10 | 2021-10-15 | Vaibhav
L.6 | Simulations | 5 | 2021-10-10 | 2021-10-15 | Prashant
L.7 | Testing on various tracks (Acceleration, Break, Greadability, endurance etc..) | 3 | 2021-10-15 | 2021-10-18 | Azaj
L.8 | Analyzing the results | 1 | 2021-10-19 | 2021-10-20 | Pravin
L.9 | Final track test | 1 | 2021-10-20 | 2021-10-21 | Azaj
M | Submission of Design reports to Captain for Package-02 | 5 | 2021-10-15 | 2021-10-20 | Pravin
M.1 | Submission of Sub-Systems reports to captain | 1 | 2021-09-15 | 2021-09-16 | Abhishek
M.2 | IPG model parameters | 2 | 2021-09-16 | 2021-09-18 | Harsh
M.3 | CAD/CAE & design reports | 2 | 2021-10-17 | 2021-10-19 | Azaj
M.4 | B-Plan, innovation report | 2 | 2021-10-17 | 2021-10-19 | Arunima
M.5 | Updating reports as per the team discussion | 2 | 2021-09-18 | 2021-09-20 | Saloni
M.6 | Submission of Package-02 | 1 | 2021-10-19 | 2021-10-20 | Pravin
N | Arranging Funds & procurement of parts | 7 | 2021-10-21 | 2021-10-28 | Abhishek
N.1 | Funds through college & sponsors |  | 2021-10-21 | 2021-10-28 | Pravin
N.2 | Roll Cage material |  | 2021-10-21 | 2021-10-28 | Harsh
N.3 | Transmission (Battery, motor, chain, pedal, Gearbox,sprockets etc..) |  | 2021-10-21 | 2021-10-28 | Prashant
N.4 | Suspension & wheel assembly (wheels, Dampers, Ball joints etc..) |  | 2021-10-21 | 2021-10-28 | Arunima
N.5 | Braking (Disc, caliper, master cylinder etc..) |  | 2021-10-21 | 2021-10-28 | Arin
N.6 | Steering ( Gear Box, knuckle joints etc..) |  | 2021-10-21 | 2021-10-28 | Abhay
N.7 | ADAS (sensors, Arduino, wire harness etc..) |  | 2021-10-21 | 2021-10-28 | Saloni
N.8 | Electricals and accessories |  | 2021-10-21 | 2021-10-28 | Saloni
O | Fabrication | 54 | 2021-11-01 | 2021-12-25 | Azaj
O.1 | Prototype | 7 | 2021-11-01 | 2021-11-08 | Harsh
O.2 | Material Testing & Analysis | 7 | 2021-11-01 | 2021-11-08 | Azaj
O.3 | Frame Building | 20 | 2021-11-09 | 2021-11-29 | Azaj
O.4 | Testing on Frame | 6 | 2021-11-29 | 2021-12-05 | Azaj
O.5 | Painting and coating on Frame | 5 | 2021-12-05 | 2021-12-10 | Harsh
O.6 | Seat Fabrication | 6 | 2021-11-29 | 2021-12-05 | Harsh
O.7 | Power train assembly | 10 | 2021-12-10 | 2021-12-20 | Pravin
O.7.1 | Motor, battery, controller, throttle | 10 | 2021-12-10 | 2021-12-20 | Prashant
O.7.2 | Gearbox, chain, sprocket, crank pedal | 10 | 2021-12-10 | 2021-12-20 | Prashant
O.8 | Wheel assembly | 10 | 2021-12-10 | 2021-12-20 | Kartik
O.8.1 | Hub & knuckle assembly | 5 | 2021-12-10 | 2021-12-15 | Kartik
O.8.2 | Installation of brakes and brake calliper on all the 4 wheels | 5 | 2021-12-10 | 2021-12-15 | Arin
O.8.3 | Integration of wheel and power train | 5 | 2021-12-15 | 2021-12-20 | Kartik
O.9 | Suspension assembly | 10 | 2021-12-10 | 2021-12-20 | Vaibhav
O.9.1 | Assembly of wishbones and damper | 6 | 2021-12-10 | 2021-12-16 | Vaibhav
O.9.2 | Assembly using ball joints | 4 | 2021-12-16 | 2021-12-20 | Arunima
O.10 | Steering assembly | 10 | 2021-12-10 | 2021-12-20 | Arpit
O.10.1 | Manufacturing of handle, tie rod etc. | 10 | 2021-12-10 | 2021-12-20 | Arpit
O.10.2 | Mechanism for Ackermann geometry | 10 | 2021-12-10 | 2021-12-20 | Abhay
O.11 | Electric circuits | 10 | 2021-12-10 | 2021-12-20 | Saloni
O.11.1 | ADAS & Infotainment | 10 | 2021-12-10 | 2021-12-20 | Saloni
O.11.2 | Safety systems | 10 | 2021-12-10 | 2021-12-20 | Saloni
O.12 | Miscellaneous | 10 | 2021-12-10 | 2021-12-20 | Harsh
O.13 | Assembly | 5 | 2021-12-20 | 2021-12-25 | Azaj
P | Physical ground testing | 9 | 2022-01-01 | 2022-01-10 | Azaj
P.1 | Design conformity test | 1 | 2022-01-01 | 2022-01-02 | Harsh
P.2 | Acceleration | 1 | 2022-01-02 | 2022-01-03 | Prashant
P.3 | Braking | 1 | 2022-01-02 | 2022-01-03 | Kartik
P.4 | Gredability | 1 | 2022-01-02 | 2022-01-03 | Prashant
P.5 | Fig of 8 | 1 | 2022-01-02 | 2022-01-03 | Abhay
P.6 | Off -roading | 1 | 2022-01-03 | 2022-01-04 | Vaibhav
P.7 | Electric Drive test | 1 | 2022-01-04 | 2022-01-05 | Prashant
P.8 | Rain shower test | 1 | 2022-01-04 | 2022-01-05 | Arunima
P.9 | Safety and ADAS | 1 | 2022-01-04 | 2022-01-05 | Saloni
P.10 | Infotainment | 1 | 2022-01-04 | 2022-01-05 | Saloni
P.11 | Endurance | 3 | 2022-01-05 | 2022-01-08 | Pravin
Q | Modification & Repairing | 5 | 2022-01-10 | 2022-01-15 | Azaj
R | Fun Drive with team | 1 | 2022-01-15 | 2022-01-16 | Pravin
S | Final Documentation | 5 | 2022-01-16 | 2022-01-21 | Pravin
T | Packaging & Shipping | 12 | 2022-01-16 | 2022-01-28 | Azaj
U | On site for event | 7 | 2022-01-31 | 2022-02-07 | Pravin
U.1 | Unpackaging | 1 | 2022-02-01 | 2022-02-02 | Harsh
U.2 | Document verification | 1 | 2022-02-02 | 2022-02-03 | Pravin
U.3 | Static testing | 1 | 2022-02-03 | 2022-02-04 | Vaibhav
U.4 | Dynamic testing | 1 | 2022-02-04 | 2022-02-05 | Pravin
U.5 | Endurance race | 1 | 2022-02-05 | 2022-02-06 | Kartik
V | Valedictory ceremony | 1 | 2022-02-06 | 2022-02-07 | Pravin
W | Back to college | 1 | 2022-02-08 | 2022-02-09 | Pravin
W.1 | Representation to College Administration | 1 | 2022-02-09 | 2022-02-10 | Pravin
W.2 | Celebration of event completion & winners | 1 | 2022-02-10 | 2022-02-11 | Pravin
Text
Team registered
Final design ready
Package 01 submitted
Final road track test
Package 02 submitted
Final Vehicle ready
Final vehicle ready for event
Completion of Event